## Automation Test Plan
Task | Planned Start Dt | Planned End Dt | Resource | Status | Progress% | Remarks/dependencies
OEM CRM - Test Automation | 2010-04-20 | 2010-05-28
EAM CRM - Feasibility Analysis | 2010-04-20 | 2010-05-01
Application Walk though | 2010-04-21 | 2010-04-22 | R1[100%],R2[50%},R3[50%] | Started | 10%
Application Level Feasibility Analysis | 2010-04-21 | 2008-10-27 | R1[100%],R2[50%},R3[50%] | Started | 10%
Test Case Level Feasibility Analysis | 2010-04-21 | 2010-04-24 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Review | 2010-04-24 | 2010-04-25 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Automation Test Strategy Definition | 2010-04-25 | 2010-04-27 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Framework Design and Customization | 2010-04-27 | 2010-04-30 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Test Environment Setup/Readiness | 2010-04-30 | 2010-05-01 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Automation Test Script Development | 2010-05-01 | 2010-05-25
Test Script Preparation | 2010-05-01 | 2010-05-16 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Test Script - Unit Testing | 2010-05-16 | 2010-05-21 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Test Script - Review | 2010-05-21 | 2010-05-23 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Test Script - Rework | 2010-05-23 | 2010-05-25 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Automation Test Script Execution | 2010-05-25 | 2010-05-28
Automated Test Script Execution & Validation | 2010-05-25 | 2010-05-28 | R1[100%],R2[50%},R3[50%] | Not started | 0%
Formulas:
Planned Start Dt = [Planned Start Dt, row below]
Planned Start Dt = [Planned End Dt, row above]
Planned End Dt = [Planned Start Dt]+1
Planned End Dt = [Planned End Dt, row below]

## Complete Effort
Final Summary
Total Effort(Hrs) |  | 60.9549
Total Effort(Days) |  | 6.9
# of TC/Scripts |  | 7 |  | Total Effort |  | 60.9549
Overall Productivity |  | 0.11
Effort per script (Hrs) |  | 8.71
TC/Script Preparation Productivity |  | 0.4541
TC/Script Execution Productivity |  | 2.2826
Productivity for TCPP and TCEP based on S:M:C |  |  |  | Total Effort | Number of TC's | Productivity
| Simple | Medium | Complex
Scripting Effort for each TC | 1.2017 | 1.8667 | 2.62
Total Scripting Effort for all TC's | 1.2017 | 3.7333 | 10.48 | 15.415 | 7 | 0.4541
Execution Effort for each TC | 0.33333 | 0.36667 | 0.5
Total Execution Effort for all TC's | 0.33333 | 0.73333 | 2 | 3.0667 | 7 | 2.2826
Feasibiltiy Analysis
Framework Design & Customization
Script Development
Script Execution
1.5Weeks
1 weeks
9 Weeks
2 Weeks

## Estimates
Total # of Regression test suite | 8
Simple test cases | 1
Medium | 2
Complex | 4
Automation % | 100%
Activities | Total Unit of Work | Complexity Distribution |  |  | Total Efforts in Person Hours |  |  |  | Remarks
|  | Simple | Medium | Complex | Simple | Medium | Complex | Total
|  | 1 | 2 | 4
Analysis
High Level Functionality understanding | 7 | NA | NA | NA | NA | NA | NA | 7 | I hour avg for each feature to understand… considered 10 features
Testcase Analysis& Feasibility Report creation | 1 | 1 | 2 | 4 | 0.1 | 0.15 | 0.2 | 0.45
Automation Strategy Definition | 1 | NA | NA | NA | NA | NA | NA | 17.6 | 3 days includes planning,documentation,review and rework
Framework Design & Customization | 1 | 1 | 2 | 4 | 0.3 | 0.45 | 1 | 1.75
Subtotal | [7 empty] | 26.8
Testcase Development
Total # of Testcases | 7 | 1 | 2 | 4 | NA | NA | NA | NA
Design Effort per Test Case | 7 | 1 | 2 | 4 | 1 | 3 | 8 | 12
Test data Setup | 7 | 1 | 2 | 4 | 0.05 | 0.3 | 0.92 | 1.27
Test Script unit testing | 7 | 1 | 2 | 4 | 0.11667 | 0.33333 | 1.2 | 1.65
Test Script review and rework | 0 | NA | NA | NA | 0.058333 | 0.16667 | 0.6 | 0.495 | 30% of unit test effort
Effort saving by Reusability | 0.05 | [6 empty] | 0.77075 | 2% of effort is saved by reusability
Subtotal | [7 empty] | 14.6442
Testcase Execution
Test Environment setup & Verification | 1 | NA | NA | NA | NA | NA | NA | 8
Test Data Verification & modification | 8 | NA | NA | NA | NA | NA | NA | 0.4 | 3 mins is considered for test data Verification
Test Script Execution(2 rounds) | 8 | 1 | 2 | 4 | 0.083333 | 0.23333 | 1 | 2.6333
Results Reporting | 8 | NA | NA | NA | NA | NA | NA | 0.52667 | 5% of Execution Effort is considered for Result Reporting
Subtotal | [7 empty] | 11.56
Total | [7 empty] | 53.0042
Contingency | [7 empty] | 2.6502 | 05% of total effort
Project management | [7 empty] | 5.3004 | 10% of total effort is considered for PM activities
Grand Total | [7 empty] | 60.9549

## Perunit effort
Automation Script Development
Activties | Effort in Person Hours |  |  | Remarks
| Simple | Medium | Complex
High Level functional understanding(phr fr module) | 1
Testcase Analysis & Feasibility Report Creation | 0.1 | 0.15 | 0.2
Automation Strategy Definition | 17.6
Framework Design & Customization | 0.3 | 0.45 | 1 | Includes effort for identifying the Reuse components, Library files,Object repository setup, data parameterization
Design Effort per Test Case | 1 | 1.5 | 2 | Script preparation, BPC Creation, Master script generation,driver script generation,startup script,
Test data Setup in excel | 0.05 | 0.15 | 0.23 | 10(S), 15(M), 20(C )
Test Script unit testing | 0.11667 | 0.16667 | 0.3 | 10(S), 15(M), 20(C )
Test Script review and rework | 50% |  |  | 50% of unit test effort
Automation Script Maintenance
Activities | Effort in Person Hours |  |  | Remarks
Test Environment Verification & Setup | 8
Test Data Verification | 0.05 |  |  | 3min/test case
Test Script Execution | 0.083333 | 0.11667 | 0.25 | 5 mins for simple, 10 mins for medium, 15 mins complex
Results Reporting | 0.2 |  |  | 10% of script execution
Productivity | S | M | C
Framework design | 0.3 | 0.45 | 1
Design+ Test Data Setup+ Unit Testing | 1.1667 | 1.8167 | 2.53
Test Script Review and Rework | 0.035 | 0.05 | 0.09
Scripting Effort for S, M & C TC | 1.2017 | 1.8667 | 2.62
Total Scripting Effort for all test cases | 1.2017 | 3.7333 | 10.48
Script Execution for S, M & C TC | 0.33333 | 0.36667 | 0.5
Total Execution Effort for all test cases | 0.33333 | 0.73333 | 2

## Scope
SNO | E2E WorkFlows | Type | Automatable/Not Automatable | Complexity | TC's
1 | Opportunity ID generation | Plugin | Yes | Medium | 2
2 | Project Name generation | Plugin | Yes | Medium | 2
3 | Audit Trail Workfolw | Plugin | Yes | Complex | 74
4 | Opportunity Assignment &Sharing ( 4 Scenarios) | Plugin | Yes | Complex | 20
5 | OSP Setup Complete(For email) ( 1 email) | Workflow | Yes | Medium | 3
6 | Workflow for CRM(For email) (16 emails) | Workflow | Yes | Complex | 48
7 | Workflow for DOC UI(For email)( 6 emails) | Workflow | Yes | Complex | 18
8 | Scheduled Email (9 emails) | Task Scheduler | Yes | Complex | 27
9 | Check OEM List(report) | SSRS Reports | No |  |  | 10
10 | Global OEM Design List(report) | SSRS Reports | No |  |  | 10
11 | MSOPS Integration | Windows Service | Yes | Medium | 2
12 | OVRP Integration | SQL Job | Yes | Complex | 7
13 | MPN Integration | Windows Service | Yes | Medium | 4
14 | Feedstore Migration ( Account entity, Opportunities, Notes, Activities) | Data Migration | No |  |  | 8
15 | UI Events | UI(Javascript events) | Not Sure ( need to check the feasibility in VSTS 2010) |  |  | 42
16 | UI Layout | UI | Not Sure ( need to check the feasibility in VSTS 2010) |  |  | 192
207